## Term Project
List | Title | Description | Points | Due | Members | Labels | Card # | Card URL
Product Backlog | Allow Game Spectators |  |  |  |  | Enhancements | 40 | https://trello.com/c/1oYefX83
Product Backlog | Play in Tournament | As a Player I want to participate in the tournament so that I can compete against other players and win. |  |  |  | Enhancements | 30 | https://trello.com/c/RTmS4lDZ
Product Backlog | Finished Game Storage | The Player must be able to store a finished game for later review. |  |  |  | Enhancements | 42 | https://trello.com/c/HFhCO4bb
Product Backlog | Multiple Simultaneous Games | The Player must be able to have multiple games in progress simultaneously. |  |  |  | Enhancements | 43 | https://trello.com/c/Gdfwcy9v
Product Backlog | Play Against an AI Opponent | The Player must be able to play a game against an AI player. |  |  |  | Enhancements | 34 | https://trello.com/c/JuKnUEBU
Product Backlog | USER STORY [Template] | Story === _As a ROLE I want to GOAL so that BENEFIT._ Story Points --- PICK ONE: 1 2 3 5 8 13 Feature Branch --- TBD |  |  |  | User Story | 59 | https://trello.com/c/fHWxKjAK
Product Backlog | SPIKE STORY [Template] | Story === _As a developer I want to learn XYZ so that I can develop the product._ Story Points --- 13 |  |  |  | Spike Story | 60 | https://trello.com/c/UDkaylI3
Ready for Dev | Force Capture Move [21] | Story === _As a System, I want to make sure that a Player has to make a capture wherever the option is available, so that I can enforce the Checkers American Rules properly._ Story Points --- 21 Feature Branch --- force-capture-move |  |  | DL | Game Play | 70 | https://trello.com/c/IMhepLdT
In Dev | Reset Turn [2] | Story === _As a Player I want to undo my entire turn before submitting it so that I can make a different play._ Story Points --- 2 Feature Branch --- reset-turn |  |  | PR | Game Play | 72 | https://trello.com/c/xW8VVnwh
In Dev | Player Resignation [2] | Story === _As a Player, I want to resign from any game of checkers so that I can play with someone else._ Story Points --- 2 Feature Branch --- player-resignation |  |  | PR | Resignation | 13 | https://trello.com/c/6qwwF4se
Ready for Test | Win Condition [13] | Story === _As a Player, I want to know if my opponent cannot make a move so that I can know if I won the game._ Story Points --- 13 Feature Branch --- win-condition |  |  | DL | Game Play | 25 | https://trello.com/c/nt1roro1
Ready for Test | Single Capture Move (King) [8] | Story === _As a Player, I want to move my piece forward, or backward, diagonally in a straight line to jump over one of my opponent's pieces so that I may capture the piece and remove it from the board._ Story Points --- 8 Feature Branch --- king-single-capture-move |  |  | ND | Game Play,Epic: King Player Moves | 56 | https://trello.com/c/57AEWAdk
Ready for Test | Non-Capturing Move (King) [5] | Story === _As a Player, I want to move my piece one space forward, or backward, diagonally so that I can move closer to my opponent's pieces._ Story Points --- 5 Feature Branch --- king-non-capturing-move |  |  | ND | Game Play,Epic: King Player Moves | 55 | https://trello.com/c/36EC65uR
Ready for Test | Multiple Capture Move (King) [5] | Story === _As a Player, I want to make more than one Single Capture Move so that I may capture my opponent's pieces and remove them from the board._ Story Points --- 5 Feature Branch --- king-multiple-capture-move |  |  | ND | Epic: King Player Moves,Game Play | 57 | https://trello.com/c/xsttJGQO
Ready for Test | EPIC: King Player Moves | Story === _As a Player, I want to move my King pieces so that I can capture or block my opponent's pieces._ |  |  |  | Epic: King Player Moves,Game Play | 66 | https://trello.com/c/3QAsxCqX
Sprint 3 done ✅ | Backup One Move [2] | Story === _As a Player I want to undo my last move before submitting my turn so that I can make a different play._ Story Points --- 2 Feature Branch --- backup-a-move |  |  | PR | Game Play | 68 | https://trello.com/c/PImHezTC
Sprint 2 done ✅ [32] | Assign Player Order [5] | Story --- As a Player, I want to know who goes first so we can play the game. Story Points --- 5 Feature Branch --- assign-player-order |  |  |  | Game Play,Epic: Set-up Game | 41 | https://trello.com/c/2SlCutBn
Sprint 2 done ✅ [32] | Manage Turn Order [3] | Story --- As a System, I want to keep track of the turn order so that I can know which Player is going to make the next move. Story Points --- 3 Feature Branch --- assign-player-order |  |  |  | Game Play | 14 | https://trello.com/c/44MWwydh
Sprint 2 done ✅ [32] | Make a Single Space Move (non-capturing) [8] | Story --- As a Player, I want to move my piece one space forward diagonally so that I can move closer to my opponent's pieces. Story Points --- 8 Feature Branch --- single-space-move |  |  |  | Game Play,Epic: Single Player Moves | 50 | https://trello.com/c/j83DlIMk
Sprint 2 done ✅ [32] | Make a Single Capture Move [8] | Story --- As a Player, I want to move my piece forward diagonally in a straight line to jump over one of my opponent's pieces so that I may capture the piece and remove it from the board. Story Points --- 8 Feature Branch --- single-capture-move |  |  |  | Epic: Single Player Moves,Game Play | 51 | https://trello.com/c/JAUsqqR8
Sprint 2 done ✅ [32] | Make a Multiple Capture Move [5] | Story --- As a Player, I want to make more than one Single Capture Move so that I may capture my opponent's pieces and remove them from the board. Story Points --- 5 Feature Branch --- multiple-capture-move |  |  |  | Epic: Single Player Moves,Game Play | 52 | https://trello.com/c/5YETSt0L
Sprint 2 done ✅ [32] | Move to King (Crowning) [3] | Story --- As a Player, I want to move my pieces to the furthest row so it may become a King piece. Story Points --- 3 Feature Branch --- move-to-king |  |  |  | Epic: Single Player Moves,Game Play | 54 | https://trello.com/c/JezYS4k6
Sprint 2 done ✅ [32] | EPIC: Set-up Game | Story --- As a Player I want to set up my game so that I can play with other online players. |  |  |  | Epic: Set-up Game | 65 | https://trello.com/c/BLUhYEZW
Sprint 2 done ✅ [32] | EPIC: Single Player Moves | Story --- As a Player, I want to move my single pieces so that I can capture or block my opponent's pieces. |  |  |  | Epic: Single Player Moves | 64 | https://trello.com/c/98kcPHfF
Sprint 1 done ✅ [70] | SPIKE: Web Architecture [13] | Story === Learn about Java Web architecture Story Points --- 13 |  |  | DL,MA,ND,PR | Spike Story | 61 | https://trello.com/c/FBbtKOae
Sprint 1 done ✅ [70] | SPIKE: Web Concurrency [13] | Story === Learn about Java Web concurrency control Story Points --- 13 |  |  | DL,MA,ND,PR | Spike Story | 62 | https://trello.com/c/KOTfhIqk
Sprint 1 done ✅ [70] | SPIKE: Domain-driven Design [13] | Story === Learn about Domain-Driven Design Story Points --- 13 |  |  | DL,MA,ND,PR | Spike Story | 63 | https://trello.com/c/KIUxt3cO
Sprint 1 done ✅ [70] | Player Sign-in [13] | Story --- As a Player I want to sign-in so that I can play a game of checkers. Story Points --- 13 Feature Branch --- sign-in |  |  |  | Sign-in | 15 | https://trello.com/c/6sUJoynw
Sprint 1 done ✅ [70] | Start a Game [13] | Story --- As a Player I want to start a game so I can challenge other online players. Story Points --- 13 Feature Branch --- start-a-game |  |  |  | Epic: Set-up Game,Game Play | 9 | https://trello.com/c/aFfPVmpP
Sprint 1 done ✅ [70] | Player Sign-out [5] | Story === As a Player, I want to sign-out so that I can end my gaming session. Story Points --- 5 Feature Branch --- sign-out |  |  |  | Sign-in | 37 | https://trello.com/c/l2JwK801

## Archived Term Project
List | Title | Description | Points | Due | Members | Labels | Card # | Card URL
[archived] MVP features | [archived] Player Resignation | Story --- As a Player, I want to resign from any game of checkers so that I can play with someone else. As a player, I must be able to resign the current game so that I can go do some other work. As a player, I must be able to quit the game when I don't want to play anymore so that I can play with someone else. Story Points --- PICK ONE: 1 2 3 5 8 13 Feature Branch --- TBD |  |  | PR | Resignation | 27 | https://trello.com/c/oCLKUcuG
Product Backlog | [archived] Decide Player Color | As a Player, I want to choose my piece color so that I can decide if I want to move first. |  |  | MA | Epic: Single Player Moves | 10 | https://trello.com/c/zyrzjFDd
Product Backlog | [archived] . | [5 empty] | 2 | https://trello.com/c/lMbE9WcJ
Product Backlog | [archived] King Player Moves (EPIC) |  |  |  |  | Epic: Single Player Moves | 12 | https://trello.com/c/Rya7FzP8
Product Backlog | [archived] Move Pieces | Story --- As a Player, I want to drag-and-drop my pieces on the board so that my opponent knows which play I made on my turn. Story Points --- PICK ONE: 1 2 3 5 8 13 Feature Branch --- TBD |  |  | DL | Epic: Set-up Game | 17 | https://trello.com/c/6gVXTSXh
Product Backlog | [archived] Make a Single Capture Move Option | Story --- As a Player, I want to decide if I want to make more than one Single Capture Move (if possible) so that I may decide when my turn ends. Story Points --- PICK ONE: 1 2 3 5 8 13 Feature Branch --- TBD |  |  |  | Epic: Single Player Moves,Game Play | 53 | https://trello.com/c/JHL0Wqya
Product Backlog | [archived] Capture Pieces | Story --- As a Player, I want to capture pieces from the other player when I “jump” over them so that I can get close to win the game. Story Points --- PICK ONE: 1 2 3 5 8 13 Feature Branch --- TBD |  |  | DL | Epic: Set-up Game | 22 | https://trello.com/c/GzXeGWUo
Product Backlog | [archived] Crow a King | Story === As a Player, I want to “crown” a piece when I reach to the furthest row. Story Points --- PICK ONE: 1 2 3 5 8 13 Feature Branch --- TBD |  |  | DL | Epic: Set-up Game | 23 | https://trello.com/c/SkmxmdPU
Product Backlog | [archived] Single Capture Move Option | Story --- As a Player, I want to decide if I want to make more than one Single Capture Move (if possible) so that I may decide when my turn ends. Story Points --- PICK ONE: 1 2 3 5 8 13 Feature Branch --- TBD |  |  |  | Game Play,Epic: King Player Moves | 58 | https://trello.com/c/cg1OKjiC
Sprint Backlog [56] | [archived] Refine User Stories |  |  | 2017-09-18 15:30 | MA,DL,ND,PR |  | 45 | https://trello.com/c/5gCdiqHJ
Sprint Backlog [56] | [archived] Develop Domain Model |  |  | 2017-09-18 15:30 | MA,DL,ND,PR |  | 46 | https://trello.com/c/6vhbxre5